## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/01 - 09/26 | Project brainstowming and planning. Created the following documents: Meeting minutes, SPPP, RiskManagement, Iteration 0 presentation, | N/A | N/A | · Decided product name: FitFusion; · Assigned personal role; · Determined tech stacks; · Set weekly meeting agenda. | N/A | N/A | N/A | N/A | N/A | 6*6 = 36 hours | 6h/person | 4 | / | / | / | / | / | / | / | Lines of Code (LOC)
1 | 09/27 - 10/17
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Jiankun Dong | Contributed to the following sections: 1. Overview 3.b non-functional requirements 5.b code commit 6.e defect management. Create Git branch for iteration 0 |  |  |  | Itereation 0, section: Goals and objectives
Haoran Zheng | SPPP_RiskManagement; Part of meeting minutes; Formulate the overall timeline of project, objectives, and deployment plan draft. |  |  |  | Iteration 0: Timeline of whole project and work summary
Yuhan Pan | Write Proposed High Level Requirements, set the theme of Nonfunctional Requirements, write the use of tools in Configuration Management Plan, determine the charts to be used, determine the metrics of Quality Assurance Plan, Code Review Process, determine the links of 7.references, |  |  |  | iteration0:Function requirenment Essential Features. Desirable Features. Optional Features

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Yunrui Huang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/19-09/26 | 7.5 | 4.5 | 3 | 0 - learn git 5 - write SPPP and define Testing method 6 - set up git | 1 |  |  |  |  | 3 | 0.5 |  | 1. Write 2 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation |  |  | 1. Break down the Requirenment to coding 2. Select the Framework we will use 3. Design the API and UI | 5

## Chengqin Li
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/19-9/24 | 8 | 5 | 3 | 0 - 1 - 2 - make project plan, send reminders to team members 3 - set up git 4 - prepare presentation 5 - Finish presentation PPT 6 - Finish Meeting Minutes Worddocx |  |  | 2 | 1 | 0.5 | 2 | 2 |  | 1. Write 2 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation 4. Write presentation PPT 5. Write Meeting Minutes Worddocx. |  |  | 0 - Continue to define requirement 1 - Presentation 2 - Continue to update SPPP 3 - Prepare for project | 6

## Jiankun Dong
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design and Implemenation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/12-09/19 | 2 | 2 | 0 | 0 - 1 - 5 - 6 - set up git 7 - research similar products | [6 empty] | 1 | 1 | 1. Setup git, make commit per lab 1 required 2. Research similar productions for project brainstorming | N/A | N?A | 5 - Implement SPPP 7 - Prepare for presentation | 6
2 | 09/20-09/26 | 5 | 2 | 3 | 0 - 1 - 5 - Work on sections of SPPP 6 - 7 - Prepare for presentaion | [5 empty] | 4 |  | 1 | 1. Work on 4 sections of SPPP 2. Helped filling progress report 3. Prepared for presentation | N/A | N/A | 0 - Learn Vue.js, Re-familiar myself with JS 1 - Design highlevel requirement 2 - Start code implemenation | 6

## Hangqi Wu
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/19-09/26 | 2 | 2 | 0 | 0 - learn git 1 - analusis what function we need 5 - make project plan and have a meeting 6 - set up git | 1 | 1 |  |  |  | 1 | 3 |  | 1. Write the PPT and meeting minutes 2. Set up git, commit a test message on git 3. Practice powerpoint presentations |  |  | 0 - continue to learn java.script 1 - continue to define requirements 3 - start some easy code | 6

## Haoran Zheng
Name: Haoran Zheng (Each student should make your own sheet to report your work weekly.)
My Role in group: Team leader.
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time(hours)
1 | 09/12-09/19 | 8 | 6 | 2 | 0 - Learn Git/Github, and train committing files through VSCode to remote Github. 1 - Determine the framework of project, 5 - Make project plan and meeting minutes. 6 - Set up git, create branch. 7 - Prepare presentation and docs. | 1 | 1.5 |  |  |  | 1 | 0.5 | 2 | 1. Write Part 3. of SPPP. 2. Set up git and test commitment. 3. Decide team roles. | 1. not familar with Git-related operations, need tutorial. 2. Haven't decide tech stacks to use. | Watch Github tutorials; Hold more group meetings next week to determine together what tech stacks we can and hope to apply. | 0 - Learning Git 1 - Determine tech stacks 2 - Determine name of our project and task distribution | 6
2 | 09/20-09/26 | 9 | 6 | 3 | 0 - Try create + merge branch on Github to seperate work spaces. 1 - Define project name and tech stacks. 2 - Frontend initialize. 5 - Create Jira group, try divide task regions. 6 - Download, test and learn MongoDB. 7 - Practice presentation for Iter 0. | 1 | 1 | 1 |  |  | 0.5 | 1 | 1.5 | 1. Finished SPPP risk management and part of meeting minutes records. 2. Distribute presentation parts of iteration 0. 3. Created Jira group and invite group members. | 1. Not very familiar with the workflow or creating a product like imagined. 2. Need more practice in presentation. | Download and learn required softwares/services; Find lessons on required skills; Practice Jira more to make better task assignment and time management. | 0 - Learn MongoDB and SQL. 1 - Analyse user's potential requirements. 2 - Design user story to attract. 5 - Set more detailed work distribution through meetings. 6 - Configure required system environments. | 7

## Yuhan Pan
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/12-09/19 | 2 | 2 | 0 | 0 - learning JS features 1 - define functional requirements 3 - analyszing implement requirements 5 - define nonfunctional requirement 6 - set up git 7 - research similar products | 3 | 2 |  | 2 |  | 1 | 1 | 1 | 1. Setup git, make commit per lab 1 required 2.Write Proposed High Level Requirements, 3. set the theme of Nonfunctional Requirements, | N/A | N?A | 0 - learning JS features 5 - Implement SPPP 7 - Prepare for presentation | 10
2 | 09/20-09/26 | 5 | 2 | 3 | 0 - learning mogodb features 1 - define functional requirements 3 - analyzing frontend features 5 - Work on sections of SPPP 7 - Prepare for presentaion | 4 | 2 |  | 2 |  | 3 | 1 | 1 | 1. Work on 4 sections of SPPP 2. write the use of tools in Configuration Management Plan, 3. determine the charts to be used, 4.determine the metrics of Quality Assurance Plan, Code Review Process, determine the links of 7.determine references, Prepared for presentation | N/A | N/A | 0 - Learn Vue.js, mogodb with JS 1 - Design highlevel requirement 2 - Start code implemenation | 13