## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 2024-09-19 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| Lack of motivation or responsibility | Being afraid of not capable for finishing the whole project | 1 | 3 | 2 | 5*3*2=30 | all members | / | Encourage each other to fulfill the task. | We are confident to finish the project. | Closed
Communication | duplicate work | multiple team member work on same work | 2 | 3 | 2 | 24 | Design and implementation leader | 2024-11-30 | Before finish and submit the whole plan, the overall check on duplicated work/functions will be performed. Also, periodically check will be performed before pushing each targeted function. | Waiting for 1st check. | Open
| worked on wrong components | Conflicts occur because of different IDE/programing language used by different team members. | 1 | 3 | 2 | 30 | Team leader | 2024-09-30 | We will confirm a unified IDE and front/backend tech stack to use recently. | In discussion. | Open
| useless work | Spent too much time on impractical works or unwanted functions. | 3 | 3 | 2 | 18 | Requirement leader | End of each iteration | Analyze target functions to realize and keep the content of project compact + efficient. | Check before each iteration ends. | Open
| inconsistent work | Different parts cannot fit well due to lack of communication or functionality check. | 3 | 3 | 3 | 27 | all members | Before pushing each new functions | Check code/database consistencity before releasing a certain function. | Waiting for 1st check. | Open
Requirements | unclear requirements | Don't deliver clearly what a function really hopes to bring for user/customer. | 2 | 3 | 3 | 36 | Requirement leader | Before pushing each new functions | Need detailed communication between requirement and implementation leader. | Waiting for requirement releases. | Open
| scope creep | Thinking for too much impractical functions, which are too far beyond the original purpose. | 2 | 2 | 3 | 48 | Design and implementation leader | At the start of each iteration. | Should formulate clearly what we can, what we want, and what we hope in future. | During function checks. | Open
| constant requirements changes | Cannot hold a firm direction of project development, hoping for adding too much. | 3 | 2 | 2 | 24 | Requirement + implementation leader | 2024-10-20 | No more features will be added after this certain date, will focus more on completing current functions. | Still deciding what to add. | Open
Management | improper task assignments | Assign team members to tasks that they are not familiar with. | 2 | 3 | 1 | 12 | Team leader | Start of each iteration | Make Excel for recording each member's skills to avoid wrong assignment. | Check before each iteration starts. | Open
| improper planning | Failing to make plan for function releasing, code integration, branch merge or file complement. | 2 | 2 | 2 | 32 | Team leader | Start of each iteration | Form a clear purposal for each iteration on who do what on what time period. | Plan in making. | Open
| lack of management skills | Team leader fail to coordinate work allocation or time distribution in each iteration. | 2 | 3 | 1 | 12 | Team leader | Start of each iteration | A clear schedule on group meeting, code testing and function assessment should be made. | Plan in making. | Open
Technology competence | Not familiar with the framework used | Lack of knowledge or teck stack skills on planning functions. | 2 | 4 | 2 | 16 | all members | 2024-09-30 | We will decide which certain tech stacks to use after taking each member's skill levels in consideration. Studys on new skills are also needed. | In discussion. | Open
| Not familiar with the programming language used | Lack of knowledge of programming languages that will be used in project. | 2 | 3 | 1 | 12 | all members | 2024-09-30 | As in previous risk, we will decide what to use after communication and skill examing. | In discussion. | Open
| Not familiar with unit testing | Not able to create test case and ensure the project works well under different environments. | 2 | 3 | 1 | 12 | Configuration leader and security leader | 2024-09-30 | Finding out which member is good at or have experience on testing products. | In discussion. | Open
| Not familiar with Git | Never paticipate in SE projects before, so no experience on using Git/Github in real working environments. | 1 | 2 | 1 | 20 | all members | 2024-09-19 | As Git is commonly required in current working environments, our team members are familiar with it, or very willing to learn more about it. | All members have learnt on how to use Git/Github with the help of Lab or external materials. | Closed
Design and implementation | Improper design | Unsatisfying user interfaces, or lacking guidance on certain functions on pages. | 2 | 3 | 3 | 36 | design and implementation leader | Before finishing the draft of Frontend design. | We will determine how many pages we will have, and what elements/functions on which page to complete the design of frontend design within several meetings. | In discussion. | Open
| improper technology stack | Select wrong tech stacks that cannot fulfill our target or user's demands. | 2 | 4 | 2 | 16 | design and implementation leader | 2024-09-30 | We will confirm exactly what kinds of tech stacks to apply recently. | In discussion. | Open
| Messy code | Code are too disordered and hard to manage/review, which will increase to cost of checking or modifying. | 2 | 3 | 4 | 48 | design and implementation leader | Before submitting each functions, and overview at the end of each iteration. | Each team member should keep their code part tidy and readable. Comments on each critical parts/functions are required for others to review and call. | Will examine at each code submission. | Open
Testing | Not enough testing | Lack of testing before releasing or submitting, which may lead to bugs on different running environments. | 2 | 3 | 3 | 36 | Configuration leader and security leader | Before final submission. | Testing on different cases or system environments will be performed to ensure least bug amount. | After each function being deployed. | Open
Integration and deployment | Not enough time for integration and deployment | Lack of sufficient knowledge on deployment of service, which may delay the release and submission of project. | 2 | 4 | 3 | 24 | all members | Before final submission. | Employing cloud services or container providers is required to fulfill the deployment of our project. | After each function being deployed. | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.